## Sheet1
| Mantis Code | Title | Status | Estimation
1 | Mantis 118495 | MVPN tab performance issue | Under investigation |  | Pending total estimation
2 | Mantis 119033 | Values with minus in CP GUI in beneficii alocate (MVPN) | Resolved | 0.25
3 | Mantis 118245 | MSISDN 0760614122 into production enviroment | Resolved | 0.5
4 | Mantis 118934 | Infocost report is not generated in Cp GUI | Under investigation | 1
5 | Mantis 118615 | Monthly refill not triggered | Resolved | 0.5
6 | Mantis 118512 | Used benefits value is not correct - For the customer CompanyID 321 the used benefits have minus values. | Resolved | 2
7 | Mantis 118494 | Unalocated benefits sum is not correct | Resolved | 2
8 | Mantis 118141 | Request failed with error: Attribute validation failed: RequiredValueMissing-SO__MEMBERREFERENCE' | Resolved | 0.5
9 | Mantis 118446 | VPN short number -In which table / column should the VPN short number be uploaded for existing customers? | Resolved | 0.125
10 | Mantis 118334 | In Corporate Portal clientul nu poate descarca factura [[in the Corporate Portal, the client can not download traffic report]] | Resolved | 0.25
11 | Mantis 118935 | [[Factura emisa report issue]] | Resolved | 0.5
12 | Mantis 119032 | export to excel it not working on CP GUI | Resolved | 0.25
13 | Mantis 118689 | [[Cosmetic changes for CR 80123]] | Resolved | 1
14 | Mantis 119126 | Factura emisa report remains in status In procesare | Resolved | 0.5
15 | Email 13/5/19 | ADD_VPN_ACCESS_SUBSCRIBER pentru compania 221 ( productie) | Resolved | 0.5
16 | Email 22/5/19 | Production pending request [[pending requests in status cancelled]] | Resolved | 0.5
17 | Email 12/6/19 | Create Company [[We have an issue with the creation of the VPN structure for the first synched customer]] | Resolved | 4
18 | Email 10/6/19 | compnay_id 68 [[Package is missing from Production DB]] | Resolved | 0.5
19 | Email 11/6/19 | Sync companyid 281 [[that all fix products are with status SYNC_FAIL]] | Resolved | 0.5
20 | Gitlab 202 | Slow performance for retrieving the existing accounts | Resolved | 1.5
21 | Skype Ciprian 19/6/19 | Question about: in which table to we have group information at MSISDN level related to call profile | Resolved | 0.125
17